# Project Progress Report

Senescence-associated hub genes in type 2 diabetes across pancreatic islet and adipose tissue

To: Dr. Kavitha Thirumurugan

From: Juvas, B.Tech Biotechnology, VIT Vellore

Date: 13 October 2026

# 1. Summary

Ma'am, the computational analysis planned in my proposal (v3) is complete. I ran it under a written protocol that was fixed and time-stamped before any expression data were analysed, with nested cross-validation and a single scoring of independent validation cohorts. The main results are:

- The senescence-gene classifiers do not generalise. In islets the honest cross-validated AUC is 0.66 (95% CI 0.53–0.79) and falls to 0.59 (0.43–0.74) in an independent cohort. In adipose tissue it is 0.53 (0.38–0.68) and 0.44 (0.14–0.74). Every external interval includes 0.5 (chance).

- No hub gene is shared between the two tissues, so no docking target met the selection rule fixed in the protocol, and docking was not performed.

- I found a data-integrity problem in public islet data. GSE38642 consists of 63 arrays that are byte-for-byte identical to arrays in GSE41762, and 11 of those donors carry a different diabetes label in each deposit. Several published papers use one of these datasets to “validate” findings from the other.

I believe this can still become a good paper, reframed around rigorous re-analysis and the reuse of public data, and I would value your guidance on the plan in section 6.

# 2. What I did

- Wrote a methodology protocol and pre-analysis plan and locked them in a version-controlled repository (git tag protocol-v1, 5 October 2026) before analysing any expression data. Every later change is dated and explained in a deviations log.

- Downloaded and verified 8 GEO datasets, normalised each one separately from raw files, and ran quality control.

- Built a senescence gene universe of 1,151 genes (SenMayo, CellAge, GenAge).

- Selected genes with LASSO, SVM-RFE and Random Forest (Boruta) strictly inside cross-validation folds (nested cross-validation), with two safety checks: a shuffled-label test for information leakage and a planted-signal test. Both passed.

- Scored the frozen models once on independent cohorts. A lock file prevents re-scoring.

- Also ran WGCNA, cross-tissue comparison, enrichment and single-cell (GSE81608) pseudobulk analysis.

| Role | Dataset | Samples (ND/T2D) | Platform |
| --- | --- | --- | --- |
| Islet discovery | GSE41762 | 57 / 20 | HuGene 1.0 ST |
| Islet validation | GSE76894 (primary) | 80 / 19 | HG-U133 Plus 2 |
| Islet validation | GSE20966 (secondary) | 10 / 10 | U133 X3P |
| Adipose discovery | GSE27951 | 11 / 12 | HG-U133 Plus 2 |
| Adipose validation | GSE71416 | 6 / 11 | HG-U133 Plus 2 |
| Adipose check | GSE16415 | 5 / 5 | ABI array |
| Single cell | GSE81608 | 1,600 cells | SMARTer |

Changes from the proposal: GSE27951 has 33 samples, not 21, so impaired-glucose-tolerance samples were excluded (n=23). GSE38642 was dropped because it duplicates GSE41762, and GSE76894 was added as a larger, independent islet validation set. ComBat was not used, because the datasets were never merged.

# 3. Key results

| Analysis | Islet AUC (95% CI) | Adipose AUC (95% CI) |
| --- | --- | --- |
| Apparent (optimistic, training data) | 0.77 (0.63–0.88) | 0.87 (0.67–1.00) |
| Nested cross-validation (honest) | 0.66 (0.53–0.79) | 0.53 (0.38–0.68) |
| Independent external cohort | 0.59 (0.43–0.74) | 0.44 (0.14–0.74) |

- Final panels were single genes: IL1R1 in islets and SNAI1 in adipose. Neither was stable across folds (42% and 46%). SNAI1 changed in the opposite direction in both adipose validation sets.

- WGCNA found one T2D-linked islet module (hubs GPC3 and FGF2). The adipose WGCNA stopped by the pre-set rule, because 23 samples do not support a reliable network.

- Single-cell analysis was inconclusive, with only 5–6 T2D donors per cell type.

- Removing the 11 donors whose labels conflict raised the islet AUC to 0.79 (0.69–0.88), which suggests that inconsistent diabetes labels limit accuracy. This is a hypothesis, not a finding.

# 4. Data-integrity findings

- All 63 GSE38642 raw files are identical (MD5 checksum) to GSE41762 files. Neither GEO record mentions the other.

- 10 donors labelled non-diabetic in GSE38642 are labelled T2D in GSE41762, which is half of its T2D group. Seven of them have HbA1c of 6.1–6.4%, below the 6.5% diagnostic cut-off.

- A 2018 paper (Li et al., Diabetes Metab Syndr Obes) noted that the samples overlap. Several later papers, from 2021 to 2026, still treat the two as independent cohorts. A first screen found 7 such papers among 9 readable ones.

- I also checked the literature: the IL-1 signal behind IL1R1 was already reported by the authors of GSE41762 (Mahdi et al. 2012, Cell Metabolism). I will cite these and not present them as new.

# 5. What this means for the original aims

The proposal expected validated senescence hub genes in each tissue, shared genes between tissues, and docking of naringenin, embelin, rutin and LSC against a prioritised target. The data do not support the first two aims, so I have not done docking. Docking a compound onto a gene that failed validation would be the first point reviewers question. The ligand structures are ready if a validated target emerges later. The LSC structure is still needed from the lab.

# 6. Proposed plan for publication

I propose one paper about how public islet data are reused and how much accuracy is overstated, with our pre-registered analysis as the core. To strengthen it, I plan three additional analyses, registered on OSF before any new data are opened:

- Overlap map: check which public islet datasets share donors (starting with GSE50397 and GSE76895).

- Literature audit: systematically record how published papers use these datasets, with a second independent reviewer.

- Leakage demonstration: compare the commonly used pipeline with ours on a fresh independent cohort (GSE76895).

Proposed timeline: analyses until late November, manuscript until mid-December, submission by mid-January 2027. Possible journals, in order: Patterns (Cell Press), Diabetologia, Briefings in Bioinformatics, with PLOS ONE or PeerJ as a fallback.

# 7. Points where I need your guidance

- Your review of the protocol, the deviations log and the full results report (attached).

- Whether you agree to leave docking out of this paper and keep it for future work.

- Your preference for the target journal, and whether the lab can support a publication fee.

- Permission to write to the submitters of GSE41762 and GSE38642 (Lund University) and to GEO about the duplicated datasets.

- A labmate who could act as the second reviewer for the literature audit.

- Authorship order and the AI-use statement (see below).

# 8. Use of AI assistance

I used an AI assistant (Claude, Anthropic) to write and run the analysis code and to draft documents, under my direction. I made the study decisions, and every step is logged in the repository. The manuscript will disclose this, as journals require. I am re-running the full pipeline from a clean copy to confirm the results reproduce exactly, and I will make sure I can explain each step.

# 9. Main limitations

- Small cohorts (adipose n=23; validation n=17–99), so confidence intervals are wide. The results show no evidence of a generalisable classifier at these sizes; they do not prove there is no effect.

- Bulk adipose tissue cannot identify which cell type drives any change.

- Cross-platform transfer and different islet preparations weaken external validation.

- All data are cross-sectional, so no causal conclusions are possible.

# Attachments

- Full results report (results/report/15_report.html)

- Methodology protocol, pre-analysis plan and deviations log

- Status and publication plan (docs/publication_plan_2026-10-12.html)

- Code repository: private GitHub repository, access available on request